## Sheet2
Black Pearl Productions
Task # | Task | Status | Owner | Estimated Effort (days) | Target Date | Comments
1 | Share respository details | Completed | Amir Ghaderi | 0 | 2019-04-02
2 | Arrange the first group meeting | Completed | Amir Ghaderi | 0 | 2019-04-02 | Metting arranged for April 28, 2019
3 | Izzat to share the youtube photography link | Pending | Izzat Sandhu | 0.5 | 2019-04-05
4 | Instagram page Logo upload | Pending | Izzat Sandhu | 0.5 | 2019-04-06
5 | Look into different editing technologies | Pending | Ankit Khirwadkar | 2 | 2019-04-12
6 | Shoot Videos/Photos of your own Condo/House | Pending | All | 4 | 2019-04-13 | To be discussed in the meeting on April 28, 2019
7 | Watch Youtube videos about photography | Pending | All | 2 | 2019-04-15
8 | Watch Youtube videos about your camera | Pending | All | 2 | 2019-04-15
9 | Watch Youtube videos about shooting wedding photography | Pending | All | 2 | 2019-04-15
10 | Watch Youtube videos about shooting real-estate photography | Pending | All | 2 | 2019-04-15
11 | Watch Youtube videos about shooting professional photography | Pending | All | 2 | 2019-04-15
12 | Take photographs of Ankit's Condo | Pending | All | 3 | 2019-04-28
13 | Take video of Ankit's Condo | Pending | Izzat Sandhu | 3 | 2019-04-28
14 | Select Couples for outdoor video/photo shoot | Pending | All | 1 | 2019-04-29
15 | Edit Photographs of Ankit's Condo | Pending | Ankit Khirwadkar | 3 | 2019-05-05
16 | Edit Video of Ankit's Condo- Highlight Video | Pending | Ankit Khirwadkar | 3 | 2019-05-05
17 | Shoot Couples for outdoor video/photo shoot/select location | Pending | All | 5 | 2019-05-12
18 | Take photographs of Amir's Condo | Pending | All | 3 | 2019-05-19
19 | Take video of Amir's Condo | Pending | Izzat Sandhu | 3 | 2019-05-19
20 | Edit Photographs of Amir's Condo | Pending | Ankit Khirwadkar | 3 | 2019-05-26
21 | Edit Video of Amir's Condo- Highlight Video | Pending | Ankit Khirwadkar | 3 | 2019-05-26
22 | Upload Photots/Videos to Instagram/Website | Pending | Amir/Izzat | 3 | 2019-05-29
23 | Website/Instagram Go Live | Pending | Amir/Izzat | 1 | 2019-05-31
24 | Marketing / Business Cards | Pending | All | 2 | 2019-06-08